## DONE
Activity\Dimension | Hours: | Hour's cost: | Total cost: | Days: | from 21 february till 8 March
Requirement Analysis | 72 | 60 | 4320 | 17
Software Design | 64 | 60 | 3840
Software Development | 51 | 40 | 2040
Quality Assurance | 51 | 30 | 1530
Project Management | 34 | 80 | 2720 | total hours: | 272
Total sum: | 272 |  | 14450 | check hours: | 272
|  |  |  | lack of: | 0

## FORECAST
Activity\Dimension | Hours: | Hour's cost: | Total cost:
Requirement Analysis | 160 | 60 | 9600 |  | working month: | 160
Software Design | 480 | 60 | 28800
Software Development | 1920 | 40 | 76800
Quality Assurance | 800 | 30 | 24000
Project Management | 640 | 80 | 51200
Total sum: | 4000 |  | 190400
MAGIC NUMBER:
204850